## Sheet1
name | description | checklist
Part 1: Core Setup & Binary Search Tree | Set up the core project structure and implement basic BST methods. | Import assignment3StartingCode into Eclipse;Do not modify BSTreeADT.java or Iterator.java;Create BSTreeNode<E> class;Create BSTree<E> class;Implement getRoot();Implement getHeight();Implement size();Implement isEmpty();Implement clear();Implement contains(E entry)
Part 2: BST Operations & Iterators | Complete the core BST operations and implement all iterator types. | Implement search(E entry);Implement add(E entry);Implement removeMin();Implement removeMax();Create InorderIterator<E> class;Create PreorderIterator<E> class;Create PostorderIterator<E> class;Implement hasNext() and next() in each;Use deep copy traversal to preload elements;Implement inorderIterator() in BSTree
Part 3: Word Logic & Input Handling | Create the Word class and build the CLI parsing and file reading logic. | Implement preorderIterator() in BSTree;Implement postorderIterator() in BSTree;Create Word class implementing Comparable<Word>;Override compareTo(), equals(), hashCode();Parse CLI arguments in WordTracker.java;Open input file line by line;Track and process each word;Deserialize or create BST on program start
Part 4: Output & Testing | Generate output from the BST and run both automated and manual tests. | Merge new input file into BST;Serialize BST to repository.ser;Print output based on CLI flags;Use inorderIterator() to output alphabetically;Write to output.txt if -f is present;Run provided JUnit tests;Manually test CLI input/output
Part 5: Finalization & Submission | Finalize documentation, evaluation, and submission package. | Write readMe.txt with overview and usage;Generate Javadoc with -private flag;Place Javadoc in /doc/ folder;Fill in MarkingCriteria_Assignment3.docx;Zip all deliverables into A3GroupName.zip